## Sheet1
| Seniority Level | Duration | P1 | SC2 | L1 | L1 | L1 | C1 | C1 | C1 | C1 | C1
| (Origin of the Resource) - RUH - AMM - TUN - OutSource - Group |  | RHU | RHU | RHU | RHU | RHU | RHU | AMM | RHU
| Role |  | BDM | DRM | AI Lead | DG Lead | DM Lead | AI | AI | Coordinator
Resource Name - If Available
ID | Phases | Weeks
| Qty. | 983 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
1 | Initiation Phase | 10 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Prepare Project charter | 5 | 3 | 2
| Prepare communication plan | 3 | 1 | 2
| Workshop engagement | 2 | 1 | 1
2 | Design Phase | 64 | 32 | 0 | 10 | 10 | 12 | 0 | 0 | 0 | 0 | 0
| Design AI strategy | 20 | 10 |  | 10
| Design Data Governance strategy | 20 | 10 |  |  | 10
| Design Data Management strategy | 24 | 12 |  |  |  | 12
3 | Build Phase | 900 | 200 | 100 | 0 | 0 | 0 | 200 | 200 | 200 | 0 | 0
| Design ML | 500 | 100 | 100 |  |  |  | 200 |  | 100
| Prepare CRISP model | 400 | 100 | [5 empty] | 200 | 100
4 | Final Phase | 9 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0
| Delivery of technical design documents | 6 | 2 | 2 | [5 empty] | 2
| Project handover | 3 | 1 | 1 | [5 empty] | 1
TOTALS